## Sheet1
issue no. | page | item | issue description | completion | date
1 | Home | testimonials | testimonials box needs to align to the center | y | 2019-09-19
2 | blog | color scheme | update and unify | y | 2019-09-20
3 | blog |  | add more post | y | 2019-09-20
4 | contact |  | update color scheme on all components | y | 2019-09-21
5 | contact |  | update font family | y | 2019-09-21
6 | contact |  | change submit button color | y | 2019-09-21
7 | all pages |  | add footer | y | 2019-09-20
8 | home | top image | update better image with special font | y | 2019-09-19
9 | all pages | top bar menu | add media break point - increase to 150% at larger screen size
10 | all pages | top bar menu | add media break point - increase to 150% at larger screen size
11 | all pages | top bar menu | turn off text decoration for hyperlink
12 | about |  | add large image stretch across the width | y | 2019-09-20
13 | about |  | add content about you to demonstrate your personality, skills and/or interests | y | 2019-09-20
14 | portfolio |  | update image and component alignment | y | 2019-09-20
15 | about |  | Links to professional accounts such as Github and LinkedIn | y | 2019-09-22
16 | all pages |  | place comments in the CSS and HTML code to identify each
17 | all pages |  | Implement Subresource Integrity (SRI) to enable browsers to verify that resources they fetch are delivered without unexpected manipulation.
18 | readme |  | Functionality / features | y | 2019-09-22
19 | readme |  | Tech stack (e.g. html, css, deployment platform, etc) | y | 2019-09-22
20 | readme |  | Sitemap | y | 2019-09-22
21
22
23